## Phase 1
Website Link | Project Type | Rebrand Level | Consistency Rollout Required | Website Sitemap | Asana onboarding Task | Client Folder | Figma Project Link | SEO Lead | Dev Lead | Start Date | Internal Deadline | Contracted Deadline | Current Status | Next Milestone | Key Risks | Notes
https://starshep.com/ | Existing Website | Full | TRUE |  | https://app.asana.com/1/1210460983765359/project/1210582587328225/task/1214133742644999?focus=true | https://drive.google.com/open?id=1t7xkJbvTLf2qT51lN2WeFqjRGgH77IP9&usp=drive_fs | https://www.figma.com/files/team/1304684573522326826/project/565927156?fuid=1248248037251978573 | Jack |  |  |  |  | Adhoc pages complete, Jack wants us to meet with client to ask about resource landing pages | Consistency brand roll-out of pages

## Phases 2,3,4
PHASE 2
Website Review, References & Initial Assumptions Doc: | Client Onboarding: Discovery Phase (template)
Crawl: | Starshep
SEO 3 Month Plan:
PHASE 3
Confirmed page production (SEO informed): | 3 per week/month
Confirmed page rollout (brand consistency - no seo): | 60 pages in total
Development Notes:
PHASE 4
List of questions/needs from client: | Template 1
Template 2
Template 3
Client Answers: | write notes here
PHASE 6
Proposed Due Date:
Roll Out Plan:
Do adhoc/admin pages get sent to client? | Y

## Phase 3 Page Design List
Page Name | Ready for dev | NB NOTE | Note | Design Time | To Design/Not to Design | Page Type | URL | Asana Task Link | Copy Doc Link | Figma Link | Suggested URL | Developer | Dev Link | Meta Title | Meta Description
404 | TRUE |  | New page | 30 min | To Design | Ad hoc/Admin - no copy | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944161?focus=true | https://docs.google.com/document/d/1QAnRK3GGqPogb_4hRx1W1nJOout5hkp4vGEvg2MP8Zs/edit?tab=t.0#heading=h.t71p78yzf7au | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=328-2&t=WgI0dLieEV7BBelY-1 |  | Tania
Abbragard Insurance | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/program/abbragard-insurance | https://app.asana.com/1/1210460983765359/project/1210582587328225/task/1214387925857042?focus=true | NA | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=810-1597&t=WZhva2FeViF1hMPk-1 |  | Tania | https://starshep-dev.patest.website/program/abbragard-insurance
About Us | TRUE |  |  | 30 min | To Design | Ad hoc - copy needed | https://starshep.com/about-us | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939717?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=811-6429&t=WZhva2FeViF1hMPk-1 |  | Tania | https://starshep-dev.patest.website/about-us
About Us Assurex | TRUE |  |  | 30 min | To Design | Ad hoc - copy needed | https://starshep.com/about-us/assurex-global-partner | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939719?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=809-896&t=WyG22SgDiWXMAmP5-1 |  | Tania | https://starshep-dev.patest.website/about-us/assurex-global-partner
About Us Charitable Fund | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/about-us/the-charitable-fund | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939726?focus=true | NA | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=815-9376&t=WZhva2FeViF1hMPk-1 |  | Tania | https://starshep-dev.patest.website/about-us/the-charitable-fund
About Us History | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/about-us/history | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939733?focus=true | NA | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=815-10638&t=WZhva2FeViF1hMPk-1 |  | Tania | https://starshep-dev.patest.website/about-us/history
About Us Theater Insurance | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/about-us/theater-insurance-venues-and-groups | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939735?focus=true | NA | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=819-11324&t=WZhva2FeViF1hMPk-1 |  | Tania | https://starshep-dev.patest.website/about-us/theater-insurance-venues-and-groups
ABYC New Member Benefit | FALSE |  | blog | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-partners-abyc-new-member-benefit/ |  |  |  |  | Tania | https://starshep-dev.patest.website/news/starkweather-shepley-partners-abyc-new-member-benefit
Accessibility | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/accessibility | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944226?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=510-6594&t=CfRng59noXYkbfaI-1 |  | Tania | https://starshep-dev.patest.website/accessibility
Affinity Program | FALSE |  | giving 404 error |  |  |  | https://starshep.com/program/east-boston-savings-bank-affinity-program
Areas of Specialization | FALSE |  | REMOVE - not necessary | 60 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/areas-of-specialization | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939739?focus=true
Author Page | TRUE |  | New page | 30 min | To Design | Ad hoc/Admin - no copy | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944167?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=463-1085&t=WgI0dLieEV7BBelY-1 |  | Tania
Benefits Solutions | FALSE | Client needs to provide industry-specific testimonial |  | 60 min | To Design | Service | https://starshep.com/services/benefits-solutions | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214217739167233?focus=true | https://docs.google.com/document/d/1c8KHogFMEa6GUJUILSqjASYZe-RSwJKepIaDhsWEPmo/edit?usp=sharing |  |  | Maria | https://starshep-dev.patest.website/services/benefits-solutions
Blog Landing Page | TRUE |  |  | 30 min | To Design | Blog | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944194?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=474-306&t=WgI0dLieEV7BBelY-1 |  | Tania | https://starshep-dev.patest.website/news
Blog Post Template | TRUE |  | under question | 30 min | To Design | Blog | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944196?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=485-3179&t=WgI0dLieEV7BBelY-1 |  | Tania
Business Insurance | TRUE |  |  | 60 min | To Design | Service | https://starshep.com/services/business-insurance | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214217739167209?focus=true | https://docs.google.com/document/d/1pZs72Xocj9C6MMsQEJgjQPoHOEyPnFbZG2q44ZREJyM/edit?usp=sharing |  |  | Maria | https://starshep-dev.patest.website/services/business-insurance
C-Port | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/c-port | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939747?focus=true | NA | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=824-12459&t=WZhva2FeViF1hMPk-1 |  | Tania | https://starshep-dev.patest.website/c-port
Captive Risk Solutions | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/industry/captive-risk-solutions | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939749?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=826-13214&t=WZhva2FeViF1hMPk-1 |  | Tania | https://starshep-dev.patest.website/industry/captive-risk-solutions
Careers | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/careers | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939751?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=825-1109&t=yeycNCJIkUMtcc5X-1 |  | Tania | https://starshep-dev.patest.website/careers
Claims | TRUE |  |  | 60 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/claims | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939753?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1454-2247&t=ZWHiMMa3bW47M9ED-1 |  | Tania | https://starshep-dev.patest.website/claims
Client Service | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/resources/client-service | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939762?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1064-21516&t=TiQA4rPz4FHi4ll3-1 |  | Tania | https://starshep-dev.patest.website/resources/client-service
Client Service | FALSE |  | DUPLICATE |  |  |  | https://starshep.com/services/client-services
Collection Protection | TRUE |  |  | 60 min | To Design | Informational | https://starshep.com/industry/collection-protection | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939770?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1457-6700&t=ZWHiMMa3bW47M9ED-1 |  | Tania | https://starshep-dev.patest.website/industry/collection-protection
Construction Risk Solutions | TRUE |  |  | 60 min | To Design | Informational | https://starshep.com/industry/construction-risk-solutions | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939772?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1148-813&t=4Zw6YIxUT0z7lvO9-1 |  | Tania | https://starshep-dev.patest.website/industry/construction-risk-solutions
Contact Us | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/about-us/contact-us | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944139?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=414-9&t=WgI0dLieEV7BBelY-1 |  | Tania | https://starshep-dev.patest.website/about-us/contact-us
Contact Us Benefits Solutions | FALSE |  | CAN BE DELETED | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/about-us/contact-benefits-solutions | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944115?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=435-883&t=WgI0dLieEV7BBelY-1
Contact Us Benefits Solutions HR Consulting | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Ad hoc/Admin - no copy | https://starshep.com/about-us/contact-benefits-solutions?industry=hr-consulting&id=2611
Contact Us Business Industry | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Ad hoc/Admin - no copy | https://starshep.com/about-us/contact-business-industry
Contact Us Business Insurance | FALSE |  | CAN BE DELETED | 30 min | Straight to Dev | Ad hoc/Admin - no copy | https://starshep.com/about-us/contact-business-insurance | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944145?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=435-883&t=WgI0dLieEV7BBelY-1
Contact Us Thank You | TRUE |  | New page | 30 min | To Design | Ad hoc/Admin - no copy | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944155?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=435-884&t=WgI0dLieEV7BBelY-1 |  | Tania | https://starshep-dev.patest.website/contact-us/thank-you
Disclaimer | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/disclaimer | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944208?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=494-453&t=WgI0dLieEV7BBelY-1 |  | Tania | https://starshep-dev.patest.website/disclaimer
East Providence, RI | TRUE |  |  | 60 min | To Design | Location | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214172620429726?focus=true | https://docs.google.com/document/d/11j704IctVBYZv7KL1autoQAZYWTdQedO9OzLuoDW1TQ/edit?usp=sharing | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=714-940&t=oERUfi8szwVWQC4s-1 |  | Tania | https://starshep-dev.patest.website/locations/east-providence-ri
Enterprise Insurance for Small Business | FALSE | Client needs to provide industry-specific testimonial |  | 60 min | To Design | Informational | https://starshep.com/industry/enterprise-insurance-for-small-business | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939780?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1455-3008&t=ZWHiMMa3bW47M9ED-1 |  | Tania | https://starshep-dev.patest.website/industry/enterprise-insurance-for-small-business
Events Landing Page | FALSE |  | REMOVING | 60 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/events
FAQ | TRUE |  | New page | 30 min | To SEO | Ad hoc - copy needed | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944173?focus=true | https://docs.google.com/document/d/1RwLuOUcVApuZ66z6fEeKue_4n3dgXLEYJXakAMlPvkQ/edit?usp=sharing | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=465-1399&t=WgI0dLieEV7BBelY-1 |  | Tania | https://starshep-dev.patest.website/about-us/faqs/
Featured Category | FALSE |  | Not sure if necessary | 60 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/category/featured
Ferman Group | FALSE |  | seems like a blog post | 0 | Straight to Dev | Blog | https://starshep.com/featured/starkweather-shepley-acquires-ferman-group-llc |  |  |  |  | Oleg
Financial Services | TRUE |  |  | 60 min | To Design | Informational | https://starshep.com/industry/financial-services | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939782?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1455-5535&t=ZWHiMMa3bW47M9ED-1 |  | Tania | https://starshep-dev.patest.website/industry/financial-services
Financial Solutions | FALSE |  | Duplicate | 30 min | To Design | Informational | http://starshep.com/industry/financial-services
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | http://starshep.com/forms-applications/starkweather-shepley-dental-pro
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-benefits-solutions/?industry=hr-consulting&id=2611
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=captive-risk-solutions&id=117
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=collection-protection&id=3183
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=construction-risk-solutions&id=119
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=enterprise-insurance-for-small-business&id=3206
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=financial-services&id=195
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=hospitality-risk-solutions&id=122
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=human-services&id=123
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=life-asset&id=2492
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=manufacturing-risk-solutions&id=125
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=marine-risk-solutions&id=157
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=real-estate&id=2490
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=surety-bond&id=2489
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=technology-life-science&id=2540
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=theatre-entertainment-risk-solutions&id=3535
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance/?industry=transportation-risk-solutions&id=2488
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-client-services/?industry=quote-capture-form&id=2608
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=bill-pay&id=2704
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=captive-risk-solutions&id=117
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=captive&id=2615
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=collection-protection&id=3183
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=communications-technology&id=2612
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=compliance&id=2610
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=construction-risk-solutions&id=119
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=dental-medical&id=3141
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=elder-care-risk-solutions&id=3421
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=employee-assistance&id=2613
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=employee-benefits&id=118
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=energy-risk-solutions&id=120
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=enterprise-insurance-for-small-business&id=3206
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=financial-services&id=195
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=forms-applications&id=2561
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=franchise&id=116
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=healthcare-risk-solutions&id=121
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=hospitality-risk-solutions&id=122
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=hr-consulting&id=2611
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=human-services&id=123
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=life-asset&id=2492
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=loss-control&id=3905
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=manufacturing-risk-solutions&id=125
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=marine-risk-solutions&id=157
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=municipalities&id=2491
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=private-exchange&id=2614
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=quote-capture-form&id=2608
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=real-estate&id=2490
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=referrals&id=2609
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=request-a-certificate&id=2605
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=seafood-risk-solutions&id=2544
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=seminar-series-events&id=2607
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=submit-a-claim&id=2606
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=surety-bond&id=2489
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=technology-life-science&id=2540
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=theatre-entertainment-risk-solutions&id=3535
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us/?industry=transportation-risk-solutions&id=2488
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/bid-bond-request
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/bonding-personal-financial-statement
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/c-port-form
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/license-permit-bond-request-form
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/performing-arts-application
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/performing-arts-application/
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/sailing-form
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/service-request
Form | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/starkweather-shepley-dental-pro
Form | FALSE |  | Dev will copy template | 0 | Straight to Dev | Form | https://starshep.com/forms-applications/white-papers
Form Template | TRUE |  | This will be one of the main templates | 60 min | Straight to Dev | Form | https://starshep.com/forms-applications/insurance-quote-form | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944224?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=510-6211&t=CfRng59noXYkbfaI-1 |  | Tania | https://starshep-dev.patest.website/forms-applications/insurance-quote-form
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=captive-risk-solutions&id=117
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=collection-protection&id=3183
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=construction-risk-solutions&id=119
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=enterprise-insurance-for-small-business&id=3206
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=financial-services&id=195
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=hospitality-risk-solutions&id=122
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=human-services&id=123
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=life-asset&id=2492
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=manufacturing-risk-solutions&id=125
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=marine-risk-solutions&id=157
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=real-estate&id=2490
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=surety-bond&id=2489
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=technology-life-science&id=2540
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=theatre-entertainment-risk-solutions&id=3535
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-business-insurance?industry=transportation-risk-solutions&id=2488
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=bill-pay&id=2704
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=captive-risk-solutions&id=117
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=captive&id=2615
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=collection-protection&id=3183
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=communications-technology&id=2612
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=compliance&id=2610
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=construction-risk-solutions&id=119
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=dental-medical&id=3141
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=elder-care-risk-solutions&id=3421
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=employee-assistance&id=2613
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=employee-benefits&id=118
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=energy-risk-solutions&id=120
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=enterprise-insurance-for-small-business&id=3206
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=financial-services&id=195
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=forms-applications&id=2561
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=franchise&id=116
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=healthcare-risk-solutions&id=121
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=hospitality-risk-solutions&id=122
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=hr-consulting&id=2611
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=human-services&id=123
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=life-asset&id=2492
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=loss-control&id=3905
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=manufacturing-risk-solutions&id=125
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=marine-risk-solutions&id=157
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=municipalities&id=2491
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=private-exchange&id=2614
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=quote-capture-form&id=2608
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=real-estate&id=2490
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=referrals&id=2609
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=request-a-certificate&id=2605
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=seafood-risk-solutions&id=2544
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=seminar-series-events&id=2607
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=submit-a-claim&id=2606
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=surety-bond&id=2489
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=technology-life-science&id=2540
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=theatre-entertainment-risk-solutions&id=3535
forms | FALSE |  | CAN BE DELETED | 0 | Straight to Dev | Form | https://starshep.com/about-us/contact-us?industry=transportation-risk-solutions&id=2488
Forms & Applications Landing Page | FALSE |  | CAN BE DELETED | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/forms-applications
Header/Footer | TRUE |  | NOTE CHANGES WERE MADE ON 12th MAY - added FAQ to ABout Us drop down | 60 min | To Design | Ad hoc/Admin - no copy | No url | https://app.asana.com/1/1210460983765359/project/1210582587328225/task/1214479428727691?focus=true |  |  |  | Tania
Home | TRUE |  |  | 90 min | To Design | Home | https://starshep.com/ | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1213744640093451?focus=true | https://docs.google.com/document/d/1s4CG2JR97h9lmdl6IJNQtPyiRTXEe1zJriYvpO4eaRg/edit?tab=t.0 | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=0-1&t=1ZBHgGXTPCWggf80-1 |  | Tania | https://starshep-dev.patest.website
Hospitality Risk Solutions | TRUE |  |  | 60 min | To Design | Informational | https://starshep.com/industry/hospitality-risk-solutions | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939792?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=884-8576&t=DqIKh4hC2Mjx9cHA-1 |  | Tania | https://starshep-dev.patest.website/industry/hospitality-risk-solutions
HR Consulting | TRUE |  |  | 60 min | To Design | Informational | https://starshep.com/industry/hr-consulting | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939800?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=898-11443&t=DqIKh4hC2Mjx9cHA-1 |  | Tania | https://starshep-dev.patest.website/industry/hr-consulting
Human Services | TRUE |  |  | 60 min | To Design | Informational | https://starshep.com/industry/human-services | https://app.asana.com/1/1210460983765359/project/1210604911491408/task/1214387925939808?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=898-9164&t=DqIKh4hC2Mjx9cHA-1 |  | Tania | https://starshep-dev.patest.website/industry/human-services
Insrance Carriers | TRUE |  | designed a template | 90 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/resources/insurance-carriers | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939818?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1275-2736&t=U9hcwYok9CZ9J3Yp-1 |  | Tania | https://starshep-dev.patest.website/resources/insurance-carriers
Insure My Trip | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/program/insure-my-trip | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939835?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=817-1228&t=WyG22SgDiWXMAmP5-1 |  | Tania | https://starshep-dev.patest.website/program/insure-my-trip
Jessica Thayer | FALSE |  | seems like a blog post | 30 min | To Design | Blog | https://starshep.com/featured/jessica-thayer-is-named-a-2023-risk-insurance-power-broker |  |  |  |  | Tania | https://starshep-dev.patest.website/featured/jessica-thayer-is-named-a-2023-risk-insurance-power-broker
Life Asset | TRUE |  |  | 60 min | To Design | Informational | https://starshep.com/industry/life-asset | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939824?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=925-352&t=inZodE0zaELjZNxg-1 |  | Tania | https://starshep-dev.patest.website/industry/life-asset
Life Asset | FALSE |  | Duplication | 30 min | To Design | Informational | https://starshep.com/industry/life-asset/
Life Asset | FALSE |  | duplicate |  |  |  | https://starshep.com/resources/industry/life-asset
Loss Control | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/areas-of-specialization/loss-control | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939816?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1278-2779&t=j3j5pUtZqG0D82Zu-1 |  | Tania | https://starshep-dev.patest.website/areas-of-specialization/loss-control
Manufacturing Risk Solutions | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/industry/manufacturing-risk-solutions | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939832?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=916-1253&t=WxKRIhvn1xd7Gt5F-1 |  | Tania | https://starshep-dev.patest.website/industry/manufacturing-risk-solutions
Marine Insurance ABYC | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/program/marine-insurance-abyc | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939820?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=964-1533&t=wIzyK203izNPIFlj-1 |  | Tania | https://starshep-dev.patest.website/program/marine-insurance-abyc
Marine Insurance ABYC Allied | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/program/marine-insurance-abyc-allied | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939822?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=973-2677&t=wIzyK203izNPIFlj-1 |  | Tania | https://starshep-dev.patest.website/program/marine-insurance-abyc-allied
Marine Risk Solutions | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/industry/marine-risk-solutions | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939837?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1454-1523&t=ZWHiMMa3bW47M9ED-1 |  | Oleg | https://starshep-dev.patest.website/industry/marine-risk-solutions/
Naples, Fl | TRUE |  |  | 60 min | To Design | Location | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214172620429731?focus=true | https://docs.google.com/document/d/1ECNuBPK2utuebCKjvI7bdRMEOBkLvlIqsM92FEXSKQU/edit?usp=sharing | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=715-1458&t=w99zyRM9WWUF2fZr-1 |  | Tania | https://starshep-dev.patest.website/locations/naples-fl
Nathan Oberg | FALSE |  | seems like a blog post | 0 | Straight to Dev | Blog | https://starshep.com/featured/nathan-oberg-joins-ss-as-commercial-account-executive-for-marine-risk-solutions-practice-group |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/4131 |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/celebrating-145-years-of-community-impact-starkweather-shepley-insurance-brokerage-inc-partners-with-roger-williams-middle-school-for-exclusive-theatre-experience |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/coronavirus-alert-back-to-business |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/david-h-marsh-joins-ss-as-private-client-risk-advisor-in-naples-fl |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/educating-new-drivers-on-the-dangers-of-distracted-driving |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/elizabeth-lowe-appointed-to-starkweather-shepley-board-of-directors |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/jack-lambrecht-joins-ss-as-a-private-client-risk-advisor |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/jessica-thayer-appointed-to-the-starkweather-shepley-board-of-directors |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/jessica-thayer-is-named-a-2023-risk-insurance-power-broker |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/kiley-prime-joins-ss-as-assistant-vice-president-private-client-risk-advisor-and-equine-specialist |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/know-your-risk-hurricane-prep-101 |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/kyle-oneill-of-starkweather-shepley-named-2026-private-client-power-broker |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/matthew-leonard-joins-ss-as-a-loss-control-safety-specialist |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/michael-prentiss-named-assistant-vice-president |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/nathan-oberg-joins-ss-as-commercial-account-executive-for-marine-risk-solutions-practice-group |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/new-hire-alicia-warschauer |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/new-hire-jonathan-cuneo-for-risk-management-specialist |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/page/2 |  |  |  |  | -
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/page/3 |  |  |  |  | -
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/page/4 |  |  |  |  | -
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/page/5 |  |  |  |  | -
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/page/6 |  |  |  |  | -
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/page/7 |  |  |  |  | -
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/page/8 |  |  |  |  | -
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/patrick-meacham-appointed-to-starkweather-shepley-board-of-directors |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/providence-business-news-5-questions-with-larry-keefe |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/rachel-bendavid-joins-marthas-vineyard-insurance-a-division-of-ss |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/ramona-gray-joins-ss-as-an-account-manager-for-surety |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/randy-white-jr-joins-ss-as-loss-control-specialist |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/richard-w-anderson-elected-to-starkweather-shepley-board-of-directors |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/robert-barresi-named-senior-vice-president |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/sandra-benson-joins-starkweather-shepley |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/ss-acquires-revens-gates-insurance-inc |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/ss-corona-virus-info |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/ss-spring-prep-guide |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/ss-winter-weather-prep |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-acquires-aik2-insurance-services |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-acquires-benefit-horizons-corporation |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-acquires-ferman-group-llc |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-acquires-macdonald-vaccaro-insurance-agency |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-acquires-oneill-co-insurance-group |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-acquires-paolino-insurance-agency |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-and-its-subsidiary-companies-annual-meeting-announce-28-stakeholder-promotions-and-officer-advancements |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-and-marthas-vineyard-insurance-celebrate-20-years-of-partnership |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-announces-22-officer-appointments-and-promotions |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-announces-the-2025-promotions-and-officer-advancements |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-announces-the-addition-of-dimatteo-insurance-brokers-llc |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-appoints-three-board-members |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-earns-worksite-health-award-from-blue-cross-blue-shield-of-rhode-island-and-the-greater-providence-chamber-of-commerce |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-hires-tim-braun-as-director-information-technology |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-hosted-a-workplace-violence-seminar-to-local-organizations |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-announces-new-palm-beach-gardens-office-location |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-announces-new-strategic-alliance-with-east-boston-savings-bank |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-brokerage-inc-acquires-wilson-agency-inc |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-brokerage-inc-aligns-with-insuremytrip-for-travel-insurance-solutions |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-brokerage-inc-announces-2024-leadership-change |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-brokerage-inc-improves-on-ranking-of-100-largest-brokers-of-u-s-business |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-brokerage-inc-recognized-as-a-2025-best-practices-agency |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-brokerage-inc-recognizes-excellence-in-construction-2025 |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-brokerage-inc-strides-toward-a-better-future-at-gloria-gemma-5k |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-brokerage-welcomes-new-trustees-and-reaffirms-leadership-for-future-growth |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-honored-as-one-of-the-2020-best-places-to-work-in-rhode-island |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-named-as-one-of-the-2024-best-places-to-work-in-rhode-island |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-insurance-named-as-one-of-the-2025-best-places-to-work-in-rhode-island |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-is-awarded-affinity-partner-of-the-year-by-cape-cod-islands-association-of-realtors-cciaor |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-named-among-the-top-100-best-places-to-work-in-insurance |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-named-as-one-of-bostons-best-and-brightest-companies-for-which-to-work |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-named-as-one-of-the-best-places-to-work-in-rhode-island |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-named-as-one-of-the-best-places-to-work-in-rhode-island-2 |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-named-in-business-insurances-annual-best-places-to-work-in-insurance |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-named-in-business-insurances-annual-best-places-to-work-in-insurance-2 |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-named-top-10-in-business-insurances-annual-best-places-to-work-in-insurance |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-partners-abyc-new-member-benefit |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-promotes-liz-basile-to-real-estate-practice-group-leader |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-raises-funds-for-big-dog-ranch-rescue-at-golf-outing |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-receives-the-united-way-of-rhode-islands-partner-award |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-recognizes-excellence-in-construction |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-sponsored-and-presented-at-the-providence-business-news-cybersecurity-tech-summit |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-sponsors-and-moderates-pbn-cybersecurity-ai-tech-summit |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-sponsors-heartwarming-holiday-surprise-for-worcester-children |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-supports-brown-university-student-emergency-fund-through-local-providence-business-frog-toad |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-utilizes-cutting-edge-technology-to-simplify-the-insurance-process |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-walks-to-support-breast-cancer-awareness-at-gloria-gemma-5k |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-welcomes-chris-nadeau-as-director-of-employee-benefits |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-welcomes-dennis-leamy-as-a-commercial-risk-advisor |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-welcomes-john-zito-to-the-employee-benefits-team |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-welcomes-tiffany-tocco-to-the-financial-institutions-practice-group |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepley-welcomes-tom-rogers-to-the-human-services-practice-as-senior-vice-president |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepleys-acquires-newport-insurance |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/starkweather-shepleys-kyle-oneill-recognized-as-a-rising-star-by-chubb |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/stefanie-schoenwolff-joins-ss-as-a-commercial-lines-account-executive |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/theresa-dorsi-recognized-as-industry-leader-for-the-2022-business-women-awards-program |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/thomas-dicarlo-joins-ss-as-the-personal-lines-president |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/what-insureds-need-to-know-about-insurance-and-hurricanes |  |  |  |  | Oleg
News Blog Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/news/winterweather |  |  |  |  | Oleg
News Landing Page | FALSE |  | becoming part of resources landing | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/category/news |  |  |  |  | -
News Landing Page | FALSE |  | Duplicate | 0 |  |  | https://starshep.com/news |  |  |  |  | -
News Landing Page | FALSE |  | Duplicate |  |  |  | https://starshep.com/resources/news |  |  |  |  | Oleg
News page 2 | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/resources/news/page/2 |  |  |  |  | Oleg
News page 3 | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/resources/news/page/3 |  |  |  |  | Oleg
News page 4 | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/resources/news/page/4 |  |  |  |  | Oleg
News page 5 | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/resources/news/page/5 |  |  |  |  | Oleg
News page 6 | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/resources/news/page/6 |  |  |  |  | Oleg
News page 7 | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/resources/news/page/7 |  |  |  |  | Oleg
News page 8 | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/resources/news/page/8 |  |  |  |  | Oleg
News Page Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/category/news/page/2 |  |  |  |  | -
News Page Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/category/news/page/3 |  |  |  |  | -
News Page Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/category/news/page/4 |  |  |  |  | -
News Page Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/category/news/page/5 |  |  |  |  | -
News Page Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/category/news/page/6 |  |  |  |  | -
News Page Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/category/news/page/7 |  |  |  |  | -
News Page Post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/category/news/page/8 |  |  |  |  | -
Newsletter Archive | FALSE |  | not sure if necessary | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/resources/newsletter-archive |  |  |  |  | Tania | https://starshep-dev.patest.website/resources/newsletter-archive
Pay Your Bill | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/billpay | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944228?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=510-6819&t=CfRng59noXYkbfaI-1 |  | Tania | https://starshep-dev.patest.website/billpay
Personal Insurance | FALSE | Client needs to provide industry-specific testimonial |  | 60 min | To SEO | Service | https://starshep.com/services/personal-insurance | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939839?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1317-6457&t=wybHMTu2y9SwsXxy-1 |  | Tania | https://starshep-dev.patest.website/services/personal-insurance/
Podcast Landing | FALSE |  | becoming part of resources landing | 60 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/resources/podcast | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944220?focus=true |  |  |  | oleg | https://starshep-dev.patest.website/resources/podcast
Privacy Policy | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/privacy-policy | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944192?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=414-10&t=CfRng59noXYkbfaI-1 |  | Tania | https://starshep-dev.patest.website/privacy-policy
Private Clients | TRUE | [8 empty] | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=3280-18267&t=ZYuv0gDDfMLk9owJ-1
Program | FALSE |  | DELETE - not neccessary |  |  |  | https://starshep.com/program
Programs | FALSE |  | DELETE - not neccessary | 60 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/areas-of-specialization/programs | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939841?focus=true
Quote capturing form | FALSE |  | Dev will copy template | 0 | Straight to Dev | Form | https://starshep.com/industry/quote-capture-form |  |  |  |  | Tania | https://starshep-dev.patest.website/industry/quote-capture-form
Randy White Jr | FALSE |  | seems like a blog post | 0 | Straight to Dev | Blog | https://starshep.com/featured/randy-white-jr-joins-ss-as-loss-control-specialist |  |  |  |  | Oleg
Real Estate | TRUE |  |  | 60 min | To Design | Informational | https://starshep.com/industry/real-estate | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939843?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1278-966&t=j3j5pUtZqG0D82Zu-1 |  | Tania | https://starshep-dev.patest.website/industry/real-estate
Referral | FALSE |  | Dev will copy template | 0 | Straight to Dev | Form | https://starshep.com/referral |  |  |  |  | Tania | https://starshep-dev.patest.website/referral
Resources Landing Page | TRUE |  | Edit made on 12 May - added category "Team Members" | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/resources | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214133077944214?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=494-932&t=WgI0dLieEV7BBelY-1 |  | Tania | https://starshep-dev.patest.website/resources
Sailing School | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/sailing-school | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939845?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1078-22666&t=TiQA4rPz4FHi4ll3-1 |  | Tania | https://starshep-dev.patest.website/sailing-school
Services Landing | TRUE |  |  | 60 min | To Design | Service | https://starshep.com/services | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939855?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=879-2883&t=DqIKh4hC2Mjx9cHA-1 |  | Tania | https://starshep-dev.patest.website/services
Step Form | FALSE |  | Will do this as an example - a template | 60 min | To Design | Form | https://starshep.com/forms-applications/abyc-marine-insurance-application | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939853?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1083-23321&t=TiQA4rPz4FHi4ll3-1 |  | Tania | https://starshep-dev.patest.website/forms-applications/abyc-marine-insurance-application
Surety Bond | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/industry/surety-bond | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939857?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1455-4976&t=ZWHiMMa3bW47M9ED-1 |  | Tania | https://starshep-dev.patest.website/industry/surety-bond
Technology Life Science | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/industry/technology-life-science | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939865?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1317-5323&t=wybHMTu2y9SwsXxy-1 |  | Oleg | https://starshep-dev.patest.website/industry/technology-life-science/
Staff Bio Template | TRUE |  |  | 30 min | To Design | Ad hoc/Admin - no copy | NEW PAGEs | https://app.asana.com/1/1210460983765359/project/1210582587328225/task/1215142558552842?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=2644-1382&t=yRyPSxkIwdumRQ3Z-1
Terms & Conditions | FALSE |  | Redirects to a contact page | [6 empty] | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=510-5787&t=CfRng59noXYkbfaI-1
Theatre Entertainment Risk Solutions | TRUE |  |  | 30 min | To Design | Informational | https://starshep.com/industry/theatre-entertainment-risk-solutions | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939867?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1312-4168&t=wybHMTu2y9SwsXxy-1 |  | Oleg
Theresa Dorsi | FALSE |  | seems like a blog post | 0 | Straight to Dev | Blog | https://starshep.com/featured/theresa-dorsi-recognized-as-industry-leader-for-the-2022-business-women-awards-program |  |  |  |  | Oleg
Transportation Risk Solutions | FALSE |  |  | 30 min | To Design | Informational | https://starshep.com/industry/transportation-risk-solutions | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214387925939869?focus=true |  | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=1312-3824&t=wybHMTu2y9SwsXxy-1 |  | Oleg
Westwood, MA | TRUE |  | new page | 60 min | To Design | Location | NEW PAGE | https://app.asana.com/1/1210460983765359/project/1213555463053300/task/1214082810872212?focus=true | https://docs.google.com/document/d/1uxmanAsiOk5xfUGp4bB4Ml5xoB_eoUCjnD4ADAVH7BQ/edit?usp=sharing | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=579-105&t=aPSq36v0ehy0b5rf-1 |  | Maria | https://starshep-dev.patest.website/locations/westwood-ma
White Paper Landing Page | FALSE |  | becoming part of resources landing | 30 min | To Design | Ad hoc/Admin - no copy | https://starshep.com/white-paper
White Paper Landing Page | FALSE |  | duplicate |  |  |  | https://starshep.com/white-paper/ |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/10-considerations-for-managing-risk-with-professional-liability-insurance |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/4073 |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/aca-fix-can-afford-coverage-without-limits |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/association-health-plans-things-to-consider |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/bid-bond-must-letter |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/building-back-better-are-you-insuring-your-home-for-the-right-amount |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/building-commitment-workplace-safety |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/cyber-liability-insurance-whos-first |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/cyber-liability-knowingly-let-following-drivers-operate-car-truck |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/cyber2021 |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/employee-benefits-group-medical-captive-insurance |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/federal-mandate-for-covid-19-vaccine-whats-next-september-2021 |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/fraudulent-wire-claims-bedevil-rias-and-their-eo-insurers-in-2023 |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/hot-potato-indemnification-whats-asked |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/how-one-small-click-led-to-big-headaches-for-a-tax-and-accounting-firms |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/lessons-learned-in-business-succession-planning-as-connelly-v-united-states-unfolds |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/mitigating-cybersecurity-risk-via-insurance |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/navigating-cco-liability-risks-tips-for-staying-out-of-the-secs-crosshairs |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/need-personal-umbrella-policy |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/now-youve-seen-problem-havent-discovered-solution |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/product-recall-coverage-versus-product-recall-expense-coverage |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/risk-what-do-i-do-with-that |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/six-common-mistakes-advisers-make-when-procuring-professional-liability-insurance-and-how-to-address-them |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/six-types-people-need-life-insurance |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/state-of-the-florida-marketplace |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/the-effects-of-covid-on-the-insurance-industry |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/tips-techniques-dealing-subcontractors-certificates-insurance |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/white-paper/what-is-a-gia-or-general-indemnity-agreement-why-do-my-spouse-and-i-both-have-to-sign |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/whitepaper_type/benefits-solutions |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/whitepaper_type/business |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/whitepaper_type/business/page/2 |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/whitepaper_type/financial |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/whitepaper_type/life-asset-protection |  |  |  |  | Oleg
white paper post | FALSE |  | Dev will copy template | 0 | Straight to Dev | Blog | https://starshep.com/whitepaper_type/personal |  |  |  |  | Oleg

## Navigation
Services | Resources | Blog | About us | Contact us
Business Insurance |  |  | Careers
Personal Insurance / Private Client |  |  | Our History
Employee Benefits Solutions |  |  | The Charitable Fund
Assurex Global Partner
https://starshep.com/services | https://starshep.com/resources | https://starshep.com/blog | https://starshep.com/about-us | https://starshep.com/about-us/contact-us
https://starshep.com/services/business-insurance |  |  | https://starshep.com/careers
https://starshep.com/services/personal-insurance |  |  | https://starshep.com/about-us/history
https://starshep.com/services/benefits-solutions |  |  | https://starshep.com/about-us/the-charitable-fund
https://starshep.com/about-us/assurex-global-partner

## Navigation V2
Business Insurance |  | Personal Insurance | Employee Benefits Solutions | Resources | About us | Contact us
-> Business Insurance
Construction | Transportation |  |  |  | Careers
Human Services | Real Estate |  |  |  | Our History
Arts, Culture, & Entertainment | Hospitality |  |  |  | The Charitable Fund
Marine | Financial Institutions |  |  |  | Assurex Global Partner
Small Business Insurance | Manufacturing
Business Insurance |  | https://starshep.com/services/personal-insurance | https://starshep.com/services/benefits-solutions | Resources | https://starshep.com/about-us | https://starshep.com/about-us/contact-us
-> Business Insurance (https://starshep.com/services/business-insurance) |  |  |  | https://starshep.com/resources
https://starshep.com/industry/construction-risk-solutions | https://starshep.com/industry/transportation-risk-solutions |  |  | https://starshep.com/blog | https://starshep.com/careers
https://starshep.com/industry/human-services | https://starshep.com/industry/real-estate |  |  |  | https://starshep.com/about-us/history
https://starshep.com/industry/theatre-entertainment-risk-solutions | https://starshep.com/industry/hospitality-risk-solutions |  |  |  | https://starshep.com/about-us/the-charitable-fund
https://starshep.com/industry/marine-risk-solutions | https://starshep.com/industry/financial-services |  |  |  | https://starshep.com/about-us/assurex-global-partner
https://starshep.com/industry/enterprise-insurance-for-small-business | https://starshep.com/industry/manufacturing-risk-solutions

## locations
components page | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=631-3835&t=lwn3C8VW7Wak7p4U-1 | done
Home page | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=0-1&t=lwn3C8VW7Wak7p4U-1 | done
Naples, FL page | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=715-1458&t=lwn3C8VW7Wak7p4U-1 | done
Westwood page | https://www.figma.com/design/AjNmg90WhsifvM1FAEMYGd/Website?node-id=612-892&t=lwn3C8VW7Wak7p4U-1 | done